## Instructions
Using the Status tracker - At the end of each week, update the status of all activities completed during the week. - The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week). - Fill in hours spent on each activity during the current week. - If 5 team members each spent an hour, that counts as 5 hours. - Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks. - During the planning phases, identify the activities to be done during each week. - If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front). - For new activities, identify the type of activity - documentation, coordination, estimation etc. - At the end of each week, plan ahead for the following week Identify people responsible for each activity. - Estimate the hours needed for the activity - Error in estimation is calculated using a formula that’s already applied.
PROJECT NUMBER | 12
PROJECT NAME | IOT Dashboard and Analytics using superset
PROJECT MENTOR (sponsor) | Santosh B
TEAM MEMBERS | R.S.Subbulakshmi
Arnav Kapoor
Debojit Das
Chinni Venkata Charan
Ujwal Narayan N

## Status
PROJECT NUMBER | 12
PROJECT NAME | IOT Dashboard and Analytics using superset
PROJECT MENTOR (sponsor) | Santosh B
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (August 6- August 12)
Fix meeting with client | Coordination | Ujwal Narayan N | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | R.S.Subbulakshmi | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client meeting | Coordination | Ujwal Narayan N | 4 | 3 | Done |  | 1 | 33.3333
Learning Superset | Preparation | Arnav Kapoor | 3 | 4.5 | Ongoing |  | -1.5 | 33.3333
Week 2 (August 13 - August 19)
Learning Superset | Preparation | Debojit Das | 4 |  | Planned
Gitlab Structure Setup | Preparation | R.S.Subbulakshmi | 0.25 | 0.25 | Done |  | 0 | 0
Team Meeting | Coordination | Ujwal Narayan N | 1 | 1 | Done |  | 0 | 0
Status tracker update | Documentation | Chinni Venkata Charan | 0.25 | 0.25 | Ongoing |  | 0 | 0
Client meeting | Coordination | Arnav Kapoor | 1.5 | 1.5 | Done |  | 0 | 0
Week 3 (August 20 - August 26)
Learning Superset | Preparation | Arnav Kapoor | 3 |  | Planned
Status tracker update | Documentation | Chinni Venkata Charan | 0.5 | 0.5 | Ongoing |  | 0 | 0
Team Meeting | Coordination | R.S.Subbulakshmi | 1 |  | Ongoing
TA Mentor Meeting | Coordination | Debojit Das | 0.5 |  | Ongoing
Client meeting | Coordination | Ujwal Narayan N | 1 |  | Ongoing