## Instructions
Using the Status tracker - At the end of each week, update the status of all activities completed during the week. - The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week). - Fill in hours spent on each activity during the current week. - If 5 team members each spent an hour, that counts as 5 hours. - Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks. - During the planning phases, identify the activities to be done during each week. - If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front). - For new activities, identify the type of activity - documentation, coordination, estimation etc. - At the end of each week, plan ahead for the following week Identify people responsible for each activity. - Estimate the hours needed for the activity - Error in estimation is calculated using a formula that’s already applied.
PROJECT NUMBER | 12
PROJECT NAME | IOT Dashboard and Analytics using superset
PROJECT MENTOR (sponsor) | Santosh B
TEAM MEMBERS | R.S.Subbulakshmi
Arnav Kapoor
Debojit Das
Chinni Venkata Charan
Ujwal Narayan N

## Status
PROJECT NUMBER | 12
PROJECT NAME | IOT Dashboard and Analytics using superset
PROJECT MENTOR (sponsor) | Santosh B
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (August 6- August 12)
Fix meeting with client | Coordination | Ujwal Narayan N | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | R.S.Subbulakshmi | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client meeting | Coordination | Ujwal Narayan N | 4 | 3 | Done |  | 1 | 33.3333
Learning Superset | Preparation | Arnav Kapoor,Chinni Venkata Charan | 3 | 4.5 | Done |  | -1.5 | 33.3333
Week 2 (August 13 - August 19)
Learning Superset | Preparation | Debojit Das,R.S.Subbulakshmi,Ujwal Narayan N, | 4 | 4 | Planned |  | 0 | 0
Gitlab Structure Setup | Preparation | R.S.Subbulakshmi | 0.25 | 0.25 | Done |  | 0 | 0
Team Meeting | Coordination | Ujwal Narayan N | 1 | 1 | Done |  | 0 | 0
Status tracker update | Documentation | Chinni Venkata Charan | 0.25 | 0.25 | Done |  | 0 | 0
Client meeting | Coordination | Arnav Kapoor | 1.5 | 1.5 | Done |  | 0 | 0
Week 3 (August 20 - August 26)
Learning Superset | Preparation | Arnav Kapoor,R.S.Subbulakshmi | 3 | 2.5 | Done |  | 0.5 | 20
Status tracker update,minutes of meeting | Documentation | Chinni Venkata Charan | 0.5 | 0.5 | Done |  | 0 | 0
Project Concept Doc | Documentation | Debojit Das | 0.5 | 0.5 | Done |  | 0 | 0
Client meeting | Coordination | Ujwal Narayan N | 1 | 1.5 | Done |  | -0.5 | 33.3333
Week 4 (August 27 -September 2)
Status tracker update | Documentation | Chinni Venkata Charan | 1.5 | 2 | Delayed | Mid Sems | -0.5 | 25
Learning Superset | Preparation | R.S.Subbulakshmi,Arnav Kapoor,Chinni Venkata Charan | 4 | 3.5 | Done | Mid Sems | 0.5 | 14.2857
SRS Draft,minutes of meeting | Documentation | Ujwal Narayan N | 1.5 | 1.5 | Done |  | 0 | 0
Fix meeting with client,Learning Superset | Coordination | Debojit Das | 0.25 | 0.25 | Done
Week 5 ( September 10 – September 16)
Creating Example Dashboards | Development | Debojit Das,R.S.Subbulakshmi,Chinni Venkata Charan | 4 | 4 | Done | Got an overview on how to create dashboards | 0 | 0
Team Meeting | Coordination | Debojit Das | 0.5 | 0.5 | Done |  | 0 | 0
Status tracker update | Documentation | Chinni Venkata Charan | 0.5 | 0.5 | Done |  | 0 | 0
Login and signup | Development | Arnav Kapoor,Ujwal Narayan N | 4 | 4 | Ongoing |  | 0 | 0
Week 6 (September 17 – September 23)
Quering different kind of databases | Development | R.S.Subbulakshmi,Chinni Venkata Charan | 4 | 3 | Done | Assignments | 1 | 33.3333
Project Plan Docx,statustracker update | Documentation | Chinni Venkata Charan | 2.5 | 2.5 | Done |  | 0 | 0
Team Meeting | Coordination | R.S.Subbulakshmi | 1 | 0.5 | Done |  | 0.5 | 100
Client meeting,Creating Charts | Coordination | Debojit Das | 1 | 1 | Done
Login and signup | Development | Ujwal Narayan N,Arnav Kapoor | 4 | 4 | Ongoing |  | 0 | 0
Week 7 (September 24 -September 30)
Visualizing databases | Development | Chinni Venkata Charan | 1 | 1 | Done |  | 0 | 0
Project Plan Docx,statustracker update | Documentation | Chinni Venkata Charan,R.S.Subbulakshmi | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | R.S.Subbulakshmi | 1 | 1 | Done |  | 0 | 0
Created roles and user | Development | R.S.Subbulakshmi | 2 | 2 | Done |  | 0 | 0
Single login | Development | Ujwal Narayan N | 1 | 1 | Ongoing |  | 0 | 0
Week 8 (October 1 – October 7)
Project Plan Docx,statustracker update | Documentation | Debojit Das,R.S.Subbulakshmi,Chinni Venkata Charan | 1 | 1 | Done |  | 0 | 0
Created ppt and demo video | Documentation | Debojit Das,R.S.Subbulakshmi,Chinni Venkata Charan,Arnav Kapoor ,Ujwal Narayana | 2 |  | Ongoing
Team Meeting | Coordination | R.S.Subbulakshmi | 2 | 3 | Done |  | -1 | 33.3333
Created seperate permissions for different roles | Development | R.S.Subbulakshmi | 2 | 4 | Ongoing |  | -2 | 50
Single login | Development | Ujwal Narayan N | 1 | 1 | Ongoing |  | 0 | 0